## 1 Quote generator
# | Request / decision | Who | Status | Notes
1.1 | No account required to generate a quote | Brandon | Build | Account required only to save, get PDF, or download mockup
1.2 | Tooltip: "Don't see the option you need? Create an account for the full library" | Brandon | Build | Drives account creation
1.3 | Single page, price pinned at top, mobile-first (~75% mobile) | Brandon | Change | Price header exists in builder; confirm sticky on mobile
1.4 | 80%-of-orders options only on public gen; everything else back end | Brandon | Build | Governs every hide/show below
1.5 | Flow order: quantity → vinyl → labels → sleeve → jacket → inserts → stickers → outer wrap | Brandon/Zack | Change | Current builder is vinyl-first; labels move up; quantity moves to top
1.6 | Packages at top (short run 100/200/300 black) + "build custom" below; no landing popup | All | Change | Bill's package preview accepted as the direction; wire packages into customer view
1.7 | Package quantity restriction (e.g., 100 units only) | Bill | Change | Hide quantities per package
1.8 | Custom quantity entry field | Bill | Change | Bill said "15 minutes" — confirm it's back in
1.9 | Open dialog at end: "Anything you're looking for that you didn't see?" | Arian | Build | Free-text question field on quote
1.10 | Soft launch with a few friendly artists before opening to public | Bill | Decide | Agreed in principle; pick artists
1.11 | Public demo domain | Bill | Decide | memphispressesvinyl.com placeholder; MRP DNS for memphisrecordpressing.com/sign-in
1.12 | Prices shown are MRP's highest public price; no confidentiality concern | Brandon | Done | Confirmed, no gating needed

## 2 Vinyl
# | Request / decision | Who | Status | Notes
2.1 | Top-level categories: Black / Solid / Blends / Special Effects / Picture Disc | Brandon | Change | Replace current website-derived categories
2.2 | Black is black — remove the six sub-options | Brandon | Change
2.3 | Solid subcategories in price order: translucent, opaque, neon, glow-in-dark | Brandon | Change
2.4 | Weight (140/180) appears only for 12"; hidden for 7" and 10" | Brandon | Change
2.5 | Disc count on public gen: 1–2 (maybe trifold); 3+ back end only | Brandon/Arian | Decide | Arian wants trifold available; Brandon says "play with it"
2.6 | Blends: standard + deluxe, list all alphabetically, dropdown not tiles | Brandon/Arian | Change | Hundreds of options; no scrolling walls
2.7 | Search field prominent on colors ("know your color? search here") | Brandon | Change | Search exists in components; surface on customer side
2.8 | Shopping-style filters (color family, type) | Andrew | Build | Strongly endorsed
2.9 | Blend component-color grid to drive search/filter | Brandon | MRP | MRP to send grid of what makes up each blend
2.10 | Mockup updates live as color changes | Bill | Done | Confirmed working
2.11 | Customer can pick a type (e.g., "standard blend") for pricing without choosing a color; tooltip "pick a color to create a mockup" | Arian/Brandon | Build
2.12 | No build-your-own blends, ever | Brandon | Done | Rule confirmed
2.13 | Build-your-own splatter: base + up to 3 splatter colors from ~40 bases incl. black | Brandon | Change | Convert hex tool into constrained picker with MRP's base list
2.14 | Splatter: show top 10 combos, then "create your own" | Brandon/Adam | Build | Clear + red is the top seller
2.15 | Color-in-color: base + 1 color; hard-no rules where known; disclaimer | Brandon/Arian | Build | "Colors are visual representation only"
2.16 | Half & half, A/B side: choose color 1 + color 2 (+ splatter) | Brandon | Change | Same pattern
2.17 | Rename "ghostly" → "cloudy"; fixed effect, customer picks color only | Brandon | Change
2.18 | Galaxy under special effects, priced as special two-color, photo option | Arian/Brandon | Change | New galaxy machines; want to push usage
2.19 | Three-color A/B side: not offered publicly | Brandon | Change | Keep in back end
2.20 | Photo AND mockup both supported per color; photos uploaded without label | Brandon/Andrew | Change | Label overlays; MRP has label-off originals or Andrew Photoshops
2.21 | Fix logo centering on label (centers to imaginary circle, not groove) | Brandon | Change | Bump the M up
2.22 | Fix double-double apple orchard image | Brandon | Change | Andrew to Photoshop
2.23 | "What will mine look like?" random splatter pattern viewer | Bill | Decide | Parked idea
2.24 | Drive customers toward deluxe blends (+$0.90–0.95) | Brandon | Decide | Design goal, not a feature yet
2.25 | New-color upload: image first, then optional mockup styling | Zack/Andrew | Change | Andrew: current flow asks to change image; fix
2.26 | Bulk price edit | Lance | Build | Currently one at a time
2.27 | Splatter surcharge changed all colors below it | Andrew | Change | Verify surcharge scoping
2.28 | Everything-not-black-is-a-surcharge model | Brandon | Done | Matches their grid; liked

## 3 Labels sleeves jackets
# | Request / decision | Who | Status | Notes
3.1 | Labels: full color / B&W / blank; no finishes; move to right after vinyl | Brandon | Change
3.2 | Rename "full color sleeve" → "full color jacket" | Brandon | Change
3.3 | Jacket order: type → color (B&W/full) → paper → finish | Brandon | Change
3.4 | Jacket types public: single, wide spine, gatefold; no tip-on, no disco bag; blank removed | Brandon/Arian | Change | Keep tip-on and disco bag in back end, hidden
3.5 | Jacket finishes: standard gloss, uncoated (reverse board), UV high gloss — Brandon said "four" | Brandon | MRP | Confirm the fourth; BOM PDF coming
3.6 | Paper: 20pt public; 24pt back end only | Brandon/Arian | Change
3.7 | Printed sleeve: paper (gloss / uncoated) or board (standard gloss / uncoated / UV high gloss) | Brandon | Change | Finish options depend on paper vs board toggle
3.8 | Unprinted sleeves: plain white, plain black, polyline white, polyline black | Brandon/Arian | Change | Wording: "unprinted polyline" if using "unprinted"
3.9 | 7" sleeves: plain white/black only; no polyline | Zack | Change | Size-gated
3.10 | Rice paper, anti-static: not on public gen | Brandon | Change | Back end only
3.11 | Editable headings/labels per press (customer-facing vs internal names) | Andrew | Build

## 4 Inserts stickers wrap
# | Request / decision | Who | Status | Notes
4.1 | Insert print options: B&W 1-side, B&W 2-side, full color 1-side, full color 2-side; no mixed | Brandon | Change
4.2 | Insert paper: gloss / uncoated; single insert also gloss/uncoated board (not gatefold) | Brandon | Change
4.3 | Download cards: back end only | Brandon | Change
4.4 | Stickers: one promo sticker on public gen | Brandon | Change | Up to two + UPC in back end
4.5 | Sticker: shape (circle/square/rectangle) → size in ¼" increments, priced per sq in | Brandon | Build | Min/max from MRP grid (up to ~16–20 sq in)
4.6 | Nine-grid sticker placement | Brandon | MRP | Grid is in the BOM
4.7 | Show sticker on mockup at chosen size | Bill | Change | Concept shown; wire to real size
4.8 | UPC sticker removed from public gen entirely; ask at conversion | Brandon | Change | Back end: have one / need one / generate ($35 fee)
4.9 | Outer wrap required: shrink wrap / open-top poly / resealable poly; no "none" | Brandon/Arian | Build
4.10 | PVC deluxe bag: lives under jacket, visible only with picture disc; picture disc gets no jacket, no shrink | All | Build | Also offer in outer wrap so MRP can choose per package
4.11 | Poly bag / PVC 12¢ insertion fee folded into bag price | Brandon | Change
4.12 | Picture disc as its own package | Arian | Build

## 5 Mastering assembly
# | Request / decision | Who | Status | Notes
5.1 | No lacquer/DMM choice on public gen | Brandon/Arian | Change | Remove from customer estimate view
5.2 | Terminology: "Masters cut by Memphis" (DMM pricing baked in) vs "I'll supply my own lacquers" | Brandon | Change | Two options only
5.3 | Own lacquers: drop cutting fee, add processing fee; two-step vs three-step by quantity | Brandon | MRP | Threshold garbled in transcript ("5,000 and below" twice); confirm
5.4 | Custom orders default: 5 test pressings, 2-day shipping; no selection | Arian/Zack | Change
5.5 | Short run: no test pressings | Brandon | Done | Rule
5.6 | Assembly: single line item, computed in background | Brandon | Change | Remove itemized breakdown
5.7 | Assembly logic: sleeved record → jacket, insert → jacket; bag insertion in bag price | Brandon | MRP | MRP to write if-then rules
5.8 | Color setup fee and stamper fee rules | Arian | MRP | On Arian's Day 2 list
5.9 | Estimate reconciliation: "Masters cut" shown at $0 delta, own lacquers shows the change | Lance/Andrew | Change

## 6 Short run vs standard
# | Request / decision | Who | Status | Notes
6.1 | 100/200: short run only (single color jacket, generic sleeve, black or eco-mix, insert OK, shrink wrap) | Brandon | Build | Constrained mode
6.2 | 300: either short run or standard | Brandon | Build
6.3 | Short run: 4–6 weeks; standard: 8–10 weeks; show as selling point | Brandon | Build | Brandon: short run is a budget play, speed is the bonus
6.4 | No multi-LP on short run | Brandon | Build
6.5 | Upsell prompt when a locked option is tapped ("available in custom, +$X/unit") | Bill/Andrew | Decide | Bill likes; not confirmed by MRP
6.6 | Sticker likely coming to short run | Brandon | Decide | Future

## 7 Artwork preflight proof
# | Request / decision | Who | Status | Notes
7.1 | Template ingest + test/certify tool (MRP admin) | Bill | Done | Shown
7.2 | Customer upload against template with pass/fail | Bill | Done | Shown
7.3 | Checks: CMYK, 300 PPI, bleed, file hygiene, outlines | Bill | Done
7.4 | Add check: text below a point size | Brandon | Build | Gavin (prepress) to define threshold; no auto outline conversion
7.5 | Connect tool to Gavin's prepress team for hole-poking | Brandon | Decide | Schedule
7.6 | MRP to supply real failed files for testing | Arian | MRP | RGB is the common failure
7.7 | Proof: cropped, no guides, center hole knocked out; view online + download; track download | Brandon | Build | Mirrors their Rosellis RIP flow
7.8 | Generate POG (package orientation guide) | Brandon | Build | "One less thing for our team"
7.9 | Layers / history views | Bill | Change | History exists, not fully working
7.10 | Failed-upload upsell ("need help? we'll fix it for $X") | Bill | Decide | Well received; price TBD
7.11 | Drag-and-drop jacket builder (front/back/spine) | Bill | Build | "Done in a couple of days"; Brandon's priority 3
7.12 | Download final art with no template layer | Bill | Done | Confirmed

## 8 Audio
# | Request / decision | Who | Status | Notes
8.1 | Track upload (single, Dropbox folder, one-file album) | Bill | Done | Shown
8.2 | Auto side breaks, drag to reorder, track name cleanup | Bill | Done | Shown
8.3 | Over-length: warn, don't prohibit | Brandon | Change | Currently prohibits per Andrew
8.4 | Cutting-speed selector (33/45) with recommendation ("would fit at 45 with better quality") | Brandon/Arian | Build
8.5 | Side-length recommendations by speed and size | Brandon | MRP | Brandon sending
8.6 | PQ sheet + preflight against MRP spec | Bill | Done | Not run live; verify
8.7 | Zip download of masters | Bill | Done

## 9 Estimates pipeline
# | Request / decision | Who | Status | Notes
9.1 | Estimate email + web view with quantity toggles | Bill | Done | Shown; Brandon received one
9.2 | Rep name on estimate (auto from sender or generic) | Bill | Decide | Which default
9.3 | "Prospects" bucket: inbound public-gen accounts vs outbound sent estimates | Brandon/Andrew | Build | Marketing wants to see gen-originated volume
9.4 | Anonymous quote tracking (browser, location, count) | Bill | Build | No PII without account
9.5 | Duplicate/version an estimate after customer changes | Lance/Andrew | Build | "That's going to happen a lot"
9.6 | Estimate reference number scheme | Arian/Andrew | Decide | Current number is placeholder
9.7 | Release umbrella: multiple estimates (vinyl/CD/cassette) under one title, compare | Andrew | Change | Partly built; not live on Niina view
9.8 | Create → Estimates / Packages split in left nav; "send estimate" only where intended | Bill | Change | Bill to fix missing button
9.9 | Placeholder art on quote mockup; complementary cover color + album name if no art | Bill/Andrew | Build | Brandon: maybe jacket art only, label as color
9.10 | Show more of center label in mockup | Brandon | Change
9.11 | Quote → project → dashboard steps (art, test press, deposit, press, ship) | Bill | Done | Shown

## 10 Back end ERP Coda
# | Request / decision | Who | Status | Notes
10.1 | Input fields on order: MRP number, SO number | Lance/Arian | Build | MRP will never send SO#; they enter it
10.2 | Client matrix = etched number; customer-facing label "catalog number" | Lance/Arian | Change | Catalog number field exists and is required
10.3 | Auto-suggest catalog number (e.g., NSLP01) when artist has none | Arian/Andrew | Build
10.4 | Variant suffix (V1/V2) auto-generated on duplicated project | Arian/Andrew/Adam | Build | Editable by human
10.5 | Data model: title umbrella → format (vinyl/CD/cassette) → variants; matrix at format level | Andrew/Lance | Decide | Bill to shape
10.6 | Recommend new UPC per variant (with explanation) | Arian | Build | Copy, not enforcement
10.7 | Early phase: order creation + payment for MRP-direct customers does NOT run through GoodTunes | Lance/Arian | Decide | They need internal QuickBooks/job matching first
10.8 | Long term: standardized spec payload → drafted order in Coda | Zack | Build | Bill to map overnight; MRP has no docs
10.9 | Pricing sync with Coda; prefer ERP as source | Zack/Bill | Decide | Direction of sync, permissions
10.10 | Tiered customer pricing | Bill/MRP | Decide | Asked; no answer
10.11 | Brokered GoodTunes orders: GoodTunes is customer of record | Lance/Andrew | Done | Agreed
10.12 | Floor/iPad view: MRP#, SO#, matrix, mockup, specs per project | Bill/Andrew | Build | Future
10.13 | Memphis dashboard: define what data MRP wants | Arian | Decide | Arian has "musings" for Day 2
10.14 | Referral pipeline (invited/accepted) | Bill | Done | Shown

## 11 MRP owes us
# | Item | Owner
11.1 | BOM PDF: all component options in order, sticker nine-grid | Brandon
11.2 | Blend component-color grid | Brandon/Arian
11.3 | Base color list (~40) for splatter/color-in-color/half-and-half + hard-no combos | Arian
11.4 | Assembly if-then rules; setup fee and stamper fee rules | Brandon/Arian
11.5 | Lacquer processing: two-step/three-step quantity threshold | Brandon
11.6 | Fourth jacket finish (named three) | Brandon
11.7 | Side-length recommendations by speed/size | Brandon
11.8 | Failed art files for preflight testing | Arian
11.9 | Label-off color photos, or permission to Photoshop | Arian/Marty
11.10 | Min text point size for preflight | Gavin
11.11 | DNS for public gen | MRP IT
11.12 | Coda: any data structure / field list | Lance/Zack

## 12 Day 2 deliverable
Day 2 deliverable
Brandon expects "a deliverable by end of day tomorrow": roadmap, priorities, what's executable, delivery windows. His priority order: (1) public quote gen, (2) back end account/save/PDF/mockup, (3) drag-and-drop art builder. Start after 9 (GZ 8–9). Arian and Lance out ~4:30.